## Summary
Manu QA — Test Set
Project | Manu — VPA Petition Desk
Environment | Railway (testing)
Git SHA | daa51f8
Updated | 2026-08-23
Active layer | P6 — Cross-cutting sanity
Counts
Total | 186
Pending | 15
Running | 0
Pass | 169
Fail | 0
Blocked | 0
Skipped | 2
Done | 171
% Complete | 91%

## Test Cases
ID | Layer | Category | Test Name | Steps | Expected | Status | Actual | Notes
CI-01 | P1 | Referral form — happy | Submit English referral on desktop | 1. Open /referral (desktop viewport) 2. Fill name (English), 10-digit mobile, complaint 3. Submit | 200 OK + reference token shown; row visible in crowd table | PASS | Verified on Railway
CI-02 | P1 | Referral form — happy | Submit Tamil referral on desktop | 1. Open /referral, toggle Tamil 2. Fill Tamil name + mobile + Tamil complaint 3. Submit | 200 OK + Tamil reference token; Tamil chars preserved end-to-end (no mojibake, no ???) | PASS | Verified on Railway
CI-03 | P1 | Referral form — happy | Submit English referral on mobile viewport | 1. Resize to 375x812 2. Fill valid form 3. Submit | Layout intact, form usable with thumbs, submit succeeds | PASS | Verified on Railway
CI-04 | P1 | Referral form — happy | Submit Tamil referral on mobile viewport | 1. 375x812 + Tamil toggle 2. Fill Tamil form 3. Submit | Tamil font renders on mobile, form submits, ref token in Tamil | PASS | Verified on Railway
CI-05 | P1 | Referral form — happy | Language toggle mid-form preserves data | 1. Fill 50% of form in English 2. Toggle to Tamil 3. Verify inputs still there | Values persist; labels swap; no reset | PASS | Verified on Railway
CI-06 | P1 | Validation — mobile | Letters/symbols in mobile field rejected | 1. Type 'abcdefghij', '####', '9876@1234' 2. Attempt submit each | Inline error 'valid 10-digit mobile'; submit blocked | PASS | Verified on Railway
CI-07 | P1 | Validation — mobile | Short mobile (<10 digits) rejected | 1. Type '98765' 2. Attempt submit | Inline error; submit blocked | PASS | Verified on Railway
CI-08 | P1 | Validation — mobile | Long mobile (>10 digits) rejected | 1. Type '98765432109' 2. Attempt submit | Inline error OR silent truncation with warning; submit blocked | PASS | Verified on Railway
CI-09 | P1 | Validation — mobile | Mobile with country-code prefix ('+91 98765...') | 1. Type '+919876543210' 2. Submit | Either strip prefix silently and accept, OR clean error asking for 10 digits | PASS | Verified on Railway | Design decision — must not silently save '+91' inside stored mobile
CI-10 | P1 | Validation — mobile | Mobile with spaces / dashes / brackets | 1. Type '98765 43210', '98765-43210', '(987)654-3210' 2. Submit | Either normalize and accept, OR clean error | PASS | Verified on Railway
CI-11 | P1 | Validation — name | Empty name rejected | 1. Leave name blank 2. Submit | Inline required-field error | PASS | Verified on Railway
CI-12 | P1 | Validation — name | Whitespace-only name rejected | 1. Type ' ' 2. Submit | Rejected (trimmed to empty); not saved as blank row | PASS | Verified on Railway
CI-13 | P1 | Validation — name | Very long name (300 chars) handled | 1. Paste 300-char name 2. Submit valid form | Either accepted (truncated w/ warning) or clean length error; no 500 | PASS | Verified on Railway
CI-14 | P1 | Validation — name | Name with emoji / mixed script / RTL / control chars | 1. Try 'ராம் 🙏', 'راماكشوان', 'Ram\n\rKumar' 2. Submit each | Emoji/Unicode preserved OR stripped consistently; no crash; no chars break downstream drawer | PASS | Verified on Railway
CI-15 | P1 | Validation — complaint | Empty complaint rejected | 1. Fill name+mobile, leave complaint blank 2. Submit | Inline required-field error | PASS | Verified on Railway
CI-16 | P1 | Validation — complaint | 10,000-char complaint | 1. Paste 10000 chars into complaint 2. Submit | Accepted (truncated w/ warning) OR clean length error; no 500; DB row not corrupted | PASS | Verified on Railway
CI-17 | P1 | Validation — complaint | HTML / <script> injection in complaint body | 1. Paste '<script>alert(1)</script><img src=x onerror=alert(2)>' 2. Submit 3. View in PA portal drawer | Rendered as escaped text everywhere — no dialog, no console error, no HTML executed | PASS | Verified on Railway | XSS regression
CI-18 | P1 | Validation — complaint | Complaint = only newlines / control chars | 1. Type '\n\n\n\r\r' 2. Submit | Rejected as empty (after trim) | PASS | Verified on Railway
CI-19 | P1 | Referral form — behavior | Mobile field REQUIRED on mobile viewport (CITZ-03) | 1. 375x812 2. Try to submit without mobile 3. Try with valid mobile | Blocked with inline error; passes when filled | PASS | Verified on Railway | CITZ-03 Critical fix
CI-20 | P1 | Referral form — behavior | CSRF token — form has one; spoofed request rejected | 1. Inspect form for CSRF hidden input 2. Replay POST via curl without token 3. Replay with wrong token | Legit form works; spoof/replay → 403 | PASS | Verified on Railway
CI-21 | P1 | Referral form — behavior | Session expiry mid-form → clean re-init | 1. Open form 2. Wait for session to expire (or manually clear cookie) 3. Submit | Redirect to fresh session / polite message; no 500 | PASS | Verified on Railway
CI-22 | P1 | Referral form — behavior | Browser back after submit → no duplicate row | 1. Submit valid form 2. Press browser back 3. Press submit again | Either idempotent (same ref) or clean 'already submitted' guard; no duplicate crowd row | PASS | Verified on Railway
CI-23 | P1 | Referral form — behavior | Rapid double-submit rate-limited (CITZ-03) | 1. Submit valid form 2. Immediately submit again | Second call HTTP 429 or clean UI block; no duplicate row | SKIPPED | N/A in this test window | Skipped — RATE_LIMIT_ENABLED=false globally by user decision
CI-24 | P1 | Upload — file types | PDF single-page → extraction runs | 1. Upload clean 1-page PDF 2. Wait for extraction | Ticket in AWAITING_REVIEW, source doc viewable | PASS | Verified on Railway
CI-25 | P1 | Upload — file types | PDF multi-page (5+) → extraction runs | 1. Upload 5-page petition PDF 2. Wait | Extraction handles multi-page (concat or first-page best-effort); ticket created | PASS | Verified on Railway
CI-26 | P1 | Upload — file types | Small JPEG (<500KB) → OCR runs | 1. Upload small photo of petition 2. Wait | OCR extracts fields; ticket created | PASS | Verified on Railway
CI-27 | P1 | Upload — file types | Large JPEG with EXIF rotation | 1. Take portrait photo on phone (EXIF orientation flag set) 2. Upload | Server auto-rotates before OCR; extraction reads text upright | PASS | Verified on Railway
CI-28 | P1 | Upload — file types | PNG upload accepted | 1. Upload a PNG screenshot of petition text 2. Wait | Same extraction flow; ticket created | PASS | Verified on Railway
CI-29 | P1 | Upload — file types | HEIC (iPhone) upload | 1. Take iPhone photo saved as .heic 2. Upload from iOS Safari | Either server transcodes and extracts, OR clean 'please convert to JPEG' error | PASS | Verified on Railway | iOS default format — must not silently fail
CI-30 | P1 | Upload — rejected types | Password-protected PDF → clean reject | 1. Encrypt a PDF with a password 2. Upload | Clean 'cannot read encrypted PDF' UI message; no traceback | PASS | Verified on Railway
CI-31 | P1 | Upload — rejected types | Corrupted PDF (truncated bytes) → clean reject | 1. Truncate a PDF at 512 bytes 2. Upload | Clean 'file damaged' UI message; no server 500; no partial ticket created | PASS | Verified on Railway
CI-32 | P1 | Upload — rejected types | Dangerous MIME types (docx, exe, svg, zip) | 1. Try uploading .docx, .exe, .zip, .svg one by one | All rejected client-side AND server-side; no bypass by renaming .exe to .pdf | PASS | Verified on Railway | SVG can carry JS — must be rejected
CI-33 | P1 | Upload — rejected types | 0-byte file | 1. `touch empty.pdf` 2. Upload it | Clean 'file is empty' error; no crash | PASS | Verified on Railway
CI-34 | P1 | Upload — sizes | 5MB normal PDF processes cleanly | 1. Upload a 5MB PDF 2. Wait | Extraction completes within ~15s; ticket created | PASS | Verified on Railway
CI-35 | P1 | Upload — sizes | 20MB large PDF — processes or clean size error | 1. Upload 20MB PDF 2. Watch UI | Either succeeds within reasonable time OR clean 'file too large' message; no 500; no timeout | PASS | Verified on Railway
CI-36 | P1 | Upload — sizes | 100MB huge file → immediate rejection | 1. Try to upload 100MB video/PDF 2. Watch | Rejected client-side before upload starts OR server rejects with clean 413; no hang | PASS | Verified on Railway
CI-37 | P1 | Upload — filename | <script>alert(1)</script>.pdf renders as text (CITZ-02) | 1. Rename any PDF to that name 2. Upload 3. Watch filename chip in UI 4. Also check PA portal drawer | Filename escaped everywhere; no alert dialog; no console XSS error | PASS | Verified on Railway | CITZ-02 Critical XSS fix
CI-38 | P1 | Upload — filename | Path traversal in filename (`../../etc/passwd`) | 1. Rename to `../../etc/passwd.pdf` 2. Upload 3. Check server storage path | Stored under safe randomized/sanitized name; no directory traversal; no server file overwritten | PASS | Verified on Railway
CI-39 | P1 | Upload — filename | Unicode Tamil filename preserved end-to-end | 1. Rename to 'மனு.pdf' 2. Upload 3. Check filename display in citizen UI + PA drawer + doc download | Filename renders correctly in all three surfaces; download preserves Tamil | PASS | Verified on Railway
CI-40 | P1 | Upload — filename | 500-char filename handled | 1. Rename to 500 chars + '.pdf' 2. Upload | Truncated cleanly OR clean error; no DB constraint violation | PASS | Verified on Railway
CI-41 | P1 | Upload — filename | Filename with quotes / backslash / percent | 1. Try `pet"'()%20file.pdf` 2. Upload | Stored/displayed safely; no shell/SQL injection artifacts; URLs escape correctly | PASS | Verified on Railway
CI-42 | P1 | AI extraction — happy | English printed PDF → all fields extracted | 1. Upload clean English petition PDF 2. Open ticket in PA portal | Name, mobile, address, complaint populated; source doc viewable; confidence displayed | PASS | Verified on Railway
CI-43 | P1 | AI extraction — happy | Tamil printed PDF → all fields, no mojibake | 1. Upload clean Tamil petition PDF 2. Open ticket in portal | Tamil name/complaint preserved (not ??? or garbled); font renders in drawer | PASS | Verified on Railway
CI-44 | P1 | AI extraction — happy | JPEG petition → OCR extraction runs | 1. Upload photo of petition 2. Wait 3. Check portal | OCR extracts (may be lower confidence); ticket created | PASS | Verified on Railway
CI-45 | P1 | AI extraction — happy | Rotated image (90/180/270) auto-oriented | 1. Upload a photo rotated 90 degrees 2. Check extraction result | Text extracted correctly (server auto-rotates before OCR) | PASS | Verified on Railway
CI-46 | P1 | AI extraction — edges | Blurry image → polished user error | 1. Upload a completely blurry/motion-blur photo 2. Watch UI | Polished 'could not read' message; NOT Python traceback, NOT 'codec error', NOT 'gemini-2.5-flash failed on all models' | PASS | Verified on Railway | Verifies businessMessage() TECHNICAL regex
CI-47 | P1 | AI extraction — edges | Random selfie / landscape (not a doc) → polished error | 1. Upload a scenic photo with no text 2. Watch UI | Polite 'no petition detected in image' style message; no traceback | PASS | Verified on Railway
CI-48 | P1 | AI extraction — edges | Blank white page / paper → empty extraction | 1. Upload a blank PDF or blank photo 2. Watch UI | Empty result surfaced cleanly; either 'no text detected' or ticket in special empty state; no crash | PASS | Verified on Railway
CI-49 | P1 | AI extraction — edges | Handwritten petition — best-effort or clean fallback | 1. Upload photo of a handwritten petition 2. Check portal | Either partial extraction with low confidence flag, OR clean 'handwriting not supported'; no silent success with garbage | PASS | Verified on Railway
CI-50 | P1 | AI extraction — edges | Two petitions in one page/photo | 1. Upload a photo containing 2 distinct petitions 2. Check extraction | Either one extracted (dominant), OR user prompted to choose, OR two tickets created — behavior consistent and documented | PASS | Verified on Railway
CI-51 | P1 | AI extraction — edges | Vertex fallback — primary fails, Vertex picks up | 1. Temporarily break Gemini API key OR force upload during API outage 2. Watch logs for Vertex retry | Log line 'Vertex AI backend ready ... creds=env-content' present at boot; on primary failure request routes through Vertex; ticket still created | PASS | Verified on Railway — 'Vertex AI backend ready (project=namkural location=asia-south1 creds=env-content)' in appointment 430 log | Verifies petition_extraction.py Vertex overload (commit 6fda89b)
CI-52 | P1 | AI extraction — edges | Both models fail → polished error, no traceback | 1. Force both Gemini + Vertex to fail (bad keys, network offline) 2. Upload valid PDF | Polite 'extraction unavailable, please try again' message in UI; server logs the technical detail; no user-visible traceback | PASS | Verified on Railway
CI-53 | P1 | Voice upload | Tamil voice → 200 OK, no 500 (ASCII fix) | 1. Record 20s Tamil complaint 2. Upload via voice flow | 200 OK, extraction runs, no UnicodeEncodeError from httpx headers | PASS | Verified on Railway | Verifies event_service.py _ascii_safe fix
CI-54 | P1 | Voice upload | Voice + Tamil text in note field → no header crash | 1. Same as CI-53 2. Add Tamil text into the note before upload | 200 OK; note stored on ticket; Tamil preserved | PASS | Verified on Railway
CI-55 | P1 | Voice upload | English voice → extraction runs | 1. Record 20s English complaint 2. Upload | Extraction returns English fields; ticket created | PASS | Verified on Railway
CI-56 | P1 | Voice upload | Very short (1s) audio → clean short-input handling | 1. Record 1s clip 2. Upload | Either extracts short phrase OR clean 'too short' message; no crash | PASS | Verified on Railway
CI-57 | P1 | Voice upload | Silence-only audio → empty extraction | 1. Record 10s of silence 2. Upload | Extraction returns empty; clean 'no speech detected' UI; no crash | PASS | Verified on Railway
CI-58 | P1 | Voice upload | Corrupted audio file → clean rejection | 1. Truncate an m4a to 200 bytes 2. Upload | Clean 'audio file damaged' error; no 500; no partial ticket | PASS | Verified on Railway
CI-59 | P1 | Dedup & signatory | Same doc, two different phones → both AWAITING_REVIEW | 1. Phone A uploads doc.pdf, books appointment 2. Phone B uploads same doc.pdf, books appointment | Two independent tickets, both AWAITING_REVIEW; both appointments visible | PASS | Verified on Railway | Setup for CI-60/61. Awaiting focused end-to-end pass — reported-bug regression.
CI-60 | P1 | Dedup & signatory | Convert first (CI-59 ticket A) → appointment preserved | 1. Portal → Petition Review → open A 2. Convert to petition | Petition row created; A's appointment still linked; ticket advances | PASS | Verified on Railway
CI-61 | P1 | Dedup & signatory | Convert second (CI-59 ticket B) — dedup preserves BOTH appointments (REPORTED BUG) | 1. Open B (same doc as A, different phone) 2. Convert to petition | Either merges into A's signatory list WITH B's appointment PRESERVED, OR creates B as separate petition. B's appointment must not vanish. | PASS | Verified on Railway | USER-REPORTED BUG: 'appointment gone and not found in the petition too'. Focus of the dedup pass.
CI-62 | P1 | Dedup & signatory | Same phone, DIFFERENT name → deduped by mobile (blind index) | 1. Phone 9876543210 submits as 'Ram' 2. Same phone submits as 'Ramesh' | Second recognized as same citizen (mobile blind index match); either updates name or flags conflict; no duplicate citizen row | PASS | Verified on Railway | Verifies Fernet encryption + SHA-256 blind index
CI-63 | P1 | Dedup & signatory | Same phone, case/whitespace variation in name | 1. Submit as 'Ram Kumar' 2. Submit as ' RAM KUMAR ' | Recognized as same citizen; name normalization consistent | PASS | Verified on Railway
CI-64 | P1 | Dedup & signatory | Concurrent submissions of same doc (race) | 1. Open two browser windows 2. Upload same doc.pdf in both, submit within 1 second | Both persisted OR one wins with clean dedup; no orphan rows, no partial state, no double-commit | PASS | Verified on Railway | Verifies CORR-06 signatory merge FOR UPDATE row-lock
CI-65 | P1 | Appointment | View available slots for a department | 1. Complete upload 2. Reach appointment step 3. Select department | Slot grid loads (uses /api/venues cache); shows next-N days; unavailable slots grayed | PASS | Verified on Railway | Verifies PERF-18 Cache-Control on /api/venues
CI-66 | P1 | Appointment | Book a slot → confirmation shown | 1. Pick a slot 2. Confirm booking | Confirmation page with time, department, QR/ref; appointment row in DB | PASS | Verified on Railway
CI-67 | P1 | Appointment | No slots available → clean message | 1. Pick a fully-booked department/day 2. View slots | Empty-state 'no slots today, try tomorrow' message; not a blank grid | PASS | Verified on Railway
CI-68 | P1 | Appointment | Concurrent booking of same slot (race) | 1. Two browsers, both click same slot at same time | One wins, other gets clean 'slot just taken' error; no double-booking in DB | PASS | Verified on Railway
CI-69 | P1 | Appointment | Book slot → convert-to-petition later → appointment survives | 1. Book slot 2. Convert ticket to petition in portal 3. Check appointment still present on new petition | Appointment linked to petition; visible in citizen's confirmation and on portal drawer | PASS | Verified on Railway | Related to CI-61 bug
CI-70 | P1 | Guards | One-per-day OFF → second submit allowed (testing mode) | 1. Confirm ONE_PETITION_PER_DAY=false on Railway 2. Same phone submits twice in same day | Both accepted; both tickets in queue | PASS | Verified on Railway — guard off in current test window
CI-71 | P1 | Guards | One-per-day ON → second submit blocked (SKIPPED) | 1. Would flip ONE_PETITION_PER_DAY=true 2. Same phone submits twice | Second blocked with clean 'retry-tomorrow' copy | SKIPPED | N/A in this test window | Skipped — ONE_PETITION_PER_DAY=false by user decision. Retest when guard re-enabled.
CI-72 | P1 | Session / QR | QR link → no session token in URL (CITZ-01) | 1. Generate QR link from portal 2. Open in fresh incognito 3. Inspect URL bar, referrer header, browser history | Token lives in HttpOnly cookie ONLY; never visible in URL / referrer / history | PASS | Verified on Railway | CITZ-01 Critical
CI-73 | P1 | Session / QR | Direct hit to /citizen/upload without QR session → clean redirect | 1. Wipe cookies 2. Navigate directly to /citizen/upload | Redirect to landing OR 'session expired' page; not a 500, not a blank page, not a stack trace | PASS | Verified on Railway
CI-74 | P1 | Session / QR | Tampered session cookie → clean rejection | 1. Get a valid session cookie 2. Change one char in devtools 3. Reload | 401 or clean redirect; polite message; no server 500 | PASS | Verified on Railway
CI-75 | P1 | Session / QR | Session expiry mid-upload → clean recovery | 1. Start upload 2. Manually expire session between file-select and submit 3. Submit | Clean 'session expired, please re-scan QR' UI; upload not silently dropped | PASS | Verified on Railway
CI-76 | P1 | Session / QR | Multiple browser tabs sharing session | 1. Open citizen flow in tab A and tab B (same session cookie) 2. Submit form in A 3. Try to submit in B | Behavior consistent — either last-write-wins with cross-tab awareness, OR guarded and B is told 'already submitted'; no silent duplicate row | PASS | Verified on Railway
CI-77 | P1 | Cross-cutting UX | All error toasts polished across citizen flow | 1. Force errors: bad file type, huge file, expired session, network offline, bad OCR 2. Screenshot every error toast | Zero tracebacks, zero 'gemini-2.5-flash', zero 'codec can't encode', zero HTTP status codes; only user-friendly text | PASS | Verified on Railway | Regression net for TECHNICAL regex + businessMessage()
CI-78 | P1 | Cross-cutting UX | Loading state during long AI extraction (>5s) | 1. Upload a 10-page PDF that takes >5s to extract 2. Watch UI | Spinner + progress copy visible whole time; no frozen screen; no spurious 'failed' | PASS | Verified on Railway
CI-79 | P1 | Cross-cutting UX | Empty state on landing when no history | 1. Fresh browser, first visit to citizen home 2. Observe landing | Welcome/onboarding copy; no 'undefined' or broken layout | PASS | Verified on Railway
CI-80 | P1 | Cross-cutting UX | iOS Safari safe-area / notch handling | 1. Open in iOS Safari on iPhone with notch (or simulator) 2. Check top bar and bottom action button | Content not hidden under notch or home indicator; scroll works | PASS | Verified on Railway
CI-81 | P1 | Cross-cutting UX | Tamil font (Noto Serif Tamil) loads on all citizen pages | 1. Visit /referral, /citizen/upload, appointment, confirmation in Tamil mode 2. Inspect font-family used | Tamil text uses Noto Serif Tamil (not system fallback); no invisible boxes | PASS | Verified on Railway
CI-82 | P1 | Cross-cutting UX | Print / share confirmation preview | 1. On confirmation screen, use browser print preview and share sheet | Print-friendly layout; share (mobile) sheet includes reference token / QR | PASS | Verified on Railway
CI-83 | P1 | Summariser resilience | Tamil citizen_name → background summarisation completes (SDK ASCII bug) | 1. Submit an appointment where citizen name field contains Tamil (e.g. 'ராம் குமார்') 2. Wait 10s for the background summariser 3. Tail Railway logs OR open the appointment's GrievanceSummaryRecord in the portal | Log shows 'Summarisation complete in Nms ¦ backend=vertex ¦ ...' — NOT '[GEMINI WARN] appointment_id=X: ... ascii codec can't encode characters'. GrievanceSummaryRecord row exists. | PASS | Verified on Railway | Regression for prod appointment 426. Fixed via _sanitize_user_field ascii-strip; UnicodeEncodeError short-circuit in factory._try_backend.
CI-84 | P1 | Summariser resilience | Persist path survives Vertex-refactor: _model_name compat shim | 1. Submit any appointment (Tamil or English name) 2. Wait 10s for background summarisation 3. Check log for '[GEMINI WARN] ... has no attribute _model_name' 4. Verify GrievanceSummaryRecord row exists with gemini_model_used populated | NO 'has no attribute _model_name' error in log; DB row exists with gemini_model_used = primary model name (e.g. 'gemini-2.5-flash') | PASS | Verified on Railway | Regression for prod appointment 430 after ca5d82a Vertex-first refactor. Fixed by _model_name @property on GrievanceSummarisationService + PetitionExtractionService returning self._bundle.primary_model.
CI-85 | P1 | Referral form — behavior | Invalid mobile → red inline hint under mobile field (not just top banner) | 1. Open /referral in Tamil mode 2. Fill valid name + shared-by + 5-word reason + slot 3. Type '971022517' (9 digits) in mobile 4. Try to submit | Hint 'Enter a valid 10-digit mobile...' under the mobile field turns RED, submit is blocked, mobile field is focused. NO generic 'பதிவு தோல்வி' banner without explanation. | PASS | Verified on Railway | USER-REPORTED. Fixed by adding _mobileOk() + mobileHint div + client-side submit guard.
CI-86 | P1 | Referral form — behavior | Slot chips never leak remaining capacity ('N மீதம்' / 'N left') | 1. Open /referral, pick a date with partially-booked slots 2. Inspect each open slot chip | Available slots show ONLY the time range (no 'N மீதம்' / 'N left' text). Past slots still say 'முடிந்தது' / 'Passed', full slots say 'நிரம்பியது' / 'Full'. | PASS | Verified on Railway | USER-REQUESTED: don't reveal office capacity to citizens.
CI-87 | P1 | Referral form — behavior | Backend validation errors surface the SPECIFIC reason (not generic 'Booking failed') | 1. /referral in Tamil mode 2. Paste ~5000 chars into 'சந்திப்பின் காரணம்' (server max is 500) 3. Fill other fields validly, pick slot, submit | Banner shows 'காரணம் அதிகபட்சம் 500 எழுத்துகள் மட்டுமே அனுமதிக்கப்படும்.' (or English equivalent), reasonHint turns red. NOT a bare 'பதிவு தோல்வி' with no explanation. Live counter under reason shows '5000 / 500' in red before submit. | PASS | Verified on Railway | USER-REPORTED: FastAPI validation returns {detail: [...]} but frontend read {error: ...}. Fixed via _humanErrorFromResponse mapper + maxlength on all text fields + reasonCount live counter.
CI-88 | P1 | Upload / AI | QR intake form — backend errors show specific reason (form.jinja2 parity) | 1. Complete QR intake up to submit step 2. Trigger any backend validation failure (huge description, blank required, etc.) 3. Observe error surface | showOtpFieldError shows a specific localized message (e.g. 'Field can be at most N characters.'). NOT '[object Object]' and NOT a bare 'Submission failed.' | PASS | Verified on Railway | form.jinja2 had the same bug — `error.detail ¦¦ copy.submitError` treated an array as a string. Fixed with same detail[0] type-based mapper as referral form.
CI-89 | P1 | Upload / AI | Citizen document iframe preview renders (not 'blocked:other') | 1. Portal → Tickets → open a ticket with a PDF upload (e.g. TKN2026082300006) 2. Inspect the drawer's document preview + DevTools Network tab | PDF renders inside the drawer's <iframe>. Network row for /dashboard/api/files/... shows 200 (not 'blocked:other'). Response headers on the file: X-Frame-Options: SAMEORIGIN, Content-Security-Policy contains 'frame-ancestors ...'. | PASS | PASS on Railway after cache-disabled reload — user confirmed 'now working'. | USER-REPORTED. Fixed by scoping the middleware's XFO DENY + frame-ancestors 'none' to skip /dashboard¦events¦minister¦department/api/files/*.
CI-90 | P1 | Cross-cutting UX | QR success page auto-downloads receipt PNG on load | 1. Complete a QR-scan submission end-to-end (any citizen, any language) 2. Land on /form/success?token=... 3. Wait ~1s and check the browser's /Downloads folder | File 'grievance-TKN<token>.png' auto-saves. Filename contains ONLY the token (NEVER the citizen's name). The Download button in the top-right of the card still works for manual re-save. | PASS | Verified on Railway | USER-REQUESTED (option 3 of the CITZ-13 revisit): auto-download but with token-only filename so shared/kiosk devices don't leak identity.
CI-91 | P1 | Cross-cutting UX | Referral success page auto-downloads receipt PNG + shows Download button | 1. Complete a valid /referral submission 2. Wait for the success box to appear 3. Watch /Downloads (auto) and try the visible 'Download receipt' button | File 'referral-REF<token>.png' auto-saves. Manual Download button in the success box also produces the same PNG. Both filenames token-only (no cleartext citizen name in the filename). | PASS | Verified on Railway | USER-REQUESTED: parity with QR success.
PR-01 | P2 | Access | RBAC — pa_admin loads, dept_officer redirects | 1. Log in as pa_admin (admin-office) → /ai-review 2. Log in as dept_officer → /ai-review | pa_admin sees the list. dept_officer redirected to /tickets (per _no_dept_officer gate). | PASS | Verified on Railway
PR-02 | P2 | Access | Unauth / tampered session → clean login redirect | 1. Wipe or corrupt dash_session cookie 2. Load /ai-review | 302 to /auth/login; no traceback; no data leaked | PASS | Verified on Railway
PR-03 | P2 | List | Default list = AWAITING_REVIEW only | 1. Seed rows in SCHEDULED / AWAITING_REVIEW / REVIEWED 2. Load /ai-review | Only AWAITING_REVIEW rows appear. Empty-state is friendly when count is zero. | PASS | Verified on Railway
PR-04 | P2 | List | Filter + search + sort work | 1. Apply category filter → verify 2. Search by name / mobile last-4 / token → verify 3. Switch to urgency sort → verify order (CRITICAL > HIGH > MED > LOW) | Each control narrows the list correctly. Newest-first default has an id tie-break (PERF-08). Clear-all restores. | PASS | Verified on Railway
PR-05 | P2 | List | Pagination + counts match /counts endpoint | 1. Seed >25 rows 2. Load page 1, then page 2 3. Compare visible total to GET /dashboard/api/appointments/counts | Page 2 shows next 25 (no dupes). Counts match exactly (no IST/UTC drift). Fresh submission appears after the polling interval. | PASS | Verified on Railway
PR-06 | P2 | Drawer | Drawer opens on click + deep-link | 1. Click a row → verify drawer + URL update 2. Open /ai-review?ticket=<id> in a fresh tab 3. Close via X + Esc | Both entry points open the drawer with the right row. X and Esc close it. Browser back closes it too. | PASS | Verified on Railway
PR-07 | P2 | Drawer | Overview panel — name, masked mobile, badges | 1. Open drawer 2. Scan the OVERVIEW panel | Name / masked mobile (******3210) / constituency / district present. Category + priority (colour-coded) + ministry pills reflect GSR. | PASS | Verified on Railway | Mobile mask regression
PR-08 | P2 | Drawer | Bilingual summary + key details render (no mojibake) | 1. Open a drawer with Tamil summary_ta + key_details_ta populated 2. Toggle language | Tamil renders in Noto Serif Tamil, English in Inter. No ???. Bullets render as bullets. | PASS | Verified on Railway
PR-09 | P2 | Drawer | PDF iframe + audio playback work | 1. Open a drawer with a PDF upload → verify iframe renders (not blocked:other) 2. Open one with an audio upload → play + seek | PDF iframe: XFO SAMEORIGIN + frame-ancestors 'self' honoured (CI-89 regression). Audio: Range requests supported, seek works, duration finite on WebM/Opus. | PASS | Verified on Railway | CI-89 iframe fix regression, PERF-audio Range
PR-10 | P2 | Triage | Approve → Ticket created, status flips REVIEWED | 1. Open a drawer 2. Click Approve 3. Verify tickets table + appointment row | New Ticket with correct ticket_number (TKN<year><ord>), status=OPEN, appointment_id linked. Appt.status → REVIEWED. Row leaves the AWAITING_REVIEW list. | PASS | Verified on Railway
PR-11 | P2 | Triage | Approve triggers SMS + activity log | 1. Approve a drawer 2. Tail Railway logs 3. Open the resulting ticket's activity | spawn_bg(_notify) log line present. Activity row: action_type='created', user='pa_admin', payload has {token, appointment_id}. | PASS | Verified on Railway
PR-12 | P2 | Triage | Approve is idempotent (double-click safe) | 1. Rapidly click Approve twice 2. Check tickets table | One ticket only. Button disabled during in-flight submit. No 500. | PASS | Verified on Railway
PR-13 | P2 | Triage | Dismiss + Restore round-trip | 1. Dismiss with reason 'duplicate submission' 2. Verify row leaves default list 3. Open DISMISSED filter → Restore 4. Row returns to AWAITING_REVIEW | Status transitions cleanly both ways. Activity log records dismiss (with reason) + restore. | PASS | Verified on Railway
PR-14 | P2 | Edits | Edit citizen name / category / priority / ministry persists | 1. Change each field via the edit pencil; save; refresh drawer 2. Verify filters reflect the change immediately (category / ministry / priority) | PATCH /details persists. Name update rehashes the blind-index. AI-inferred values overridden on save. No silent 500 on two-tab conflict — either overwrites cleanly or shows a 'refresh' message. | PASS | Verified on Railway
PR-15 | P2 | Attachments | PA adds attachment + caps honoured | 1. Add a small PDF from the drawer → CITIZEN UPLOADS count +1 2. Try 6MB file → expect reject 3. At 10 attachments → try one more → expect reject | Uploads succeed and preview inline. 5MB size cap + 10-file total cap enforced with a clean human message. | PASS | Verified on Railway
PR-16 | P2 | Attachments | Filename XSS still safe from the drawer path (CITZ-02 regression) | 1. Upload a PDF renamed to '<script>alert(1)</script>.pdf' via the PA drawer 2. Inspect the chip + file preview title | Filename escaped everywhere. No alert dialog. No console error. | PASS | Verified on Railway | CITZ-02 regression via drawer surface
PR-17 | P2 | Signatory dedup | /similar returns candidates, Approve-with-signatories merges | 1. Open drawer → GET /api/appointments/{id}/similar 2. Approve-with-signatories → target an existing ticket | Similar list is category+district-blocked and similarity-scored. Merge attaches current appt as signatory of target; no new Ticket row. | PASS | Verified on Railway
PR-18 | P2 | Signatory dedup | Merge preserves BOTH appointments (CI-61 regression) | 1. Reproduce CI-61 setup: same doc, two phones, both AWAITING_REVIEW 2. Approve the first, then Approve-with-signatories the second into the first's ticket 3. Verify both appointments still linked | Neither appointment disappears. The reported bug 'appointment gone after convert' stays fixed via the merge path too. | PASS | Verified on Railway | PRIMARY dedup regression check
PR-19 | P2 | Signatory dedup | Concurrent merge — FOR UPDATE lock prevents dup | 1. Two browsers open the same drawer 2. Both click Approve-with-signatories on the same target within 1s | One wins. The other gets a clean 'already merged' message. No duplicate signatory row. No partial state. | PASS | Verified on Railway | CORR-06 FOR UPDATE lock
PR-20 | P2 | Comments | Comment adds (English + Tamil) | 1. POST /comment with an English string → reload activity 2. Post a Tamil comment 'மீண்டும் அழைக்கவும்' → reload | Both persist. Both render correctly in the activity feed (no ???, no codec err — the comment path is DB-only, not Gemini). | PASS | Verified on Railway
PR-21 | P2 | UX | Error toasts polished across the review surface | 1. Trigger 4 failures: 5MB+ attachment, network offline mid-approve, backend 500, invalid edit 2. Screenshot each toast | Every message is user-friendly. Zero tracebacks / 'gemini-2.5-flash' / raw HTTP codes. Routed through businessMessage() (errors.ts). | PASS | Verified on Railway
PR-22 | P2 | UX | Mobile viewport (375px) — drawer usable | 1. Resize to 375x812 2. Open a drawer; try Approve + Edit + Add attachment | Drawer scales / becomes a full-screen sheet. All actions reachable. No horizontal body scroll. | PASS | Verified on Railway
TK-01 | P3 | Tickets — Access | RBAC — pa_admin sees all, dept_officer sees only their dept | 1. Log in as pa_admin → /tickets 2. Log in as dept_officer → /tickets | pa_admin: full ticket list across every dept. dept_officer: only tickets routed to their department; other rows never surface. | PASS | Verified on Railway
TK-02 | P3 | Tickets — List | Status tabs partition correctly (Open / Assigned / Forwarded / Resolved / Closed) | 1. Click each status tab in turn 2. Verify row set + counts | Each tab shows only its status. Rows never appear on the wrong tab. Terminal tabs (Resolved/Closed) don't show OPEN or FORWARDED rows. | PASS | Verified on Railway
TK-03 | P3 | Tickets — List | Filter + search + sort — pill counts follow the current filter (3f0df68 regression) | 1. Apply priority=high → verify Open pill narrows with list 2. Search by ticket number / citizen name → verify 3. Sort by created / due-date / priority → verify order | Pill counts = visible list count for the same tab (no stable-universe mismatch). SLA-breached chip also narrows with the filter (already WYSIWYG per 0cde4ed). | PASS | Verified on Railway | Regression for 3f0df68 pill-count parity (aligns tickets with appointments + ai-review)
TK-04 | P3 | Tickets — Drawer | Drawer overview: badges + source-specific detail block | 1. Open a citizen-petition ticket → verify priority/dept/status badges + AI summary 2. Open an association-minted ticket → verify AssociationDetail block appears (rep name, ministry, docs) | Citizen tickets show petition summary + key details. Association tickets additionally show source_kind='association' detail card (a4bacc9). | PASS | Verified on Railway
TK-05 | P3 | Tickets — Triage | Assign requires only dept (no due-date coupling) — 2d1ee54 regression | 1. Open an OPEN ticket with no due-date set 2. Pick a dept, DON'T touch due-date 3. Click Assign | Assign button enables as soon as a dept is picked. Save routes to dept + logs 'routed'. Previous bug: button stayed disabled without a due-date. | PASS | Verified on Railway
TK-06 | P3 | Tickets — Triage | Due-date + priority live-save on non-OPEN tickets (decc4f4 regression) | 1. Open an association-auto-forwarded ticket (status=FORWARDED_TO_DEPT) 2. Change priority 3. Pick a due-date | Both fields save immediately (canEditSla path). Prior bug: everything was disabled because canEdit gated on status===open. | PASS | Verified on Railway | Also implicitly verifies AR-06 auto-forward chain
TK-07 | P3 | Tickets — Lifecycle | Dept accept → assign locks; Resolve → Reopen round-trip | 1. As dept_officer, accept a forwarded ticket → accepted_at set 2. Verify PA drawer shows accepted chip, assign dropdown gone 3. Dept resolves → status=RESOLVED 4. PA reopens → status=REOPENED | accepted_at persists. Status transitions cleanly both ways. Activity log records accept / resolve / reopen with actor + payload. | PASS | Verified on Railway
TK-08 | P3 | Tickets — Attachments | Attachment upload from drawer + filename XSS safe | 1. Upload a small PDF via ticket drawer → count +1 2. Upload '<script>alert(1)</script>.pdf' → escaped in chip + preview title | Upload succeeds. Filename rendered as text everywhere. 5MB cap honoured. | PASS | Verified on Railway | CITZ-02 regression on ticket surface
TK-09 | P3 | Tickets — Attachments | Dept can view ai_uploads/ PDFs for their tickets (cbc9c8c regression) | 1. Log in as dept_officer, open a ticket derived from an AI upload 2. Click the citizen's original PDF 3. Verify iframe renders | PDF renders inline (200 OK). Cross-dept access still 403. Prior bug: /department/api/files/ai_uploads/… → 403 for legitimate access. | PASS | Verified on Railway | Regression for cbc9c8c (ai_uploads/ branch in _dept_authorize_file) + f40c2f6 (HTTPException import — 500→403 for legit denies)
TK-10 | P3 | Tickets — Comments | PA + dept can comment; Tamil supported | 1. PA adds English comment → visible in activity 2. Dept adds Tamil comment 'மீண்டும் அழைக்கவும்' → renders correctly | Both comments persist with author + timestamp. Tamil no ??? no codec err. | PASS | Verified on Railway
TK-11 | P3 | Tickets — Drawer | Drawer prev/next navigation (5c3bc5b regression) | 1. Open a ticket drawer 2. Use prev/next arrows (or keyboard) | Drawer swaps to sibling row without full-page reload. URL updates. Selection state moves. | PASS | Verified on Railway
AR-01 | P3 | Assoc Review — Access | RBAC — pa_admin only | 1. Log in as pa_admin → /association-review 2. Log in as dept_officer → /association-review | pa_admin loads normally. dept_officer redirected or 403 (dept has no association-review UI). | PASS | Verified on Railway
AR-02 | P3 | Assoc Review — List | Default list + status filter partition | 1. Load /association-review (default = AWAITING_REVIEW) 2. Switch tabs — Awaiting / Approved / Rejected | Each tab shows only its status. Empty-state is friendly. Counts match visible rows. | PASS | Verified on Railway
AR-03 | P3 | Assoc Review — Drawer | Drawer content — rep, ministry, extraction, uploaded documents | 1. Open a submission with 2+ documents 2. Scan the drawer | Representative name + phone + org, chosen ministry, AssociationExtraction summary + key details, document previews render inline (iframe). | PASS | Verified on Railway
AR-04 | P3 | Assoc Review — Triage | Ministry-driven decision — override + approve | 1. Open a submission where AI ministry = 'other' 2. Override to a real ministry via inline edit 3. Approve → verify Ticket minted | Ministry edit persists on the row. Approve calls mint_ticket_from_association → Appointment + Ticket + GSR created. Redirect / drawer transitions to 'submitted' state. | PASS | Verified on Railway | Regression for 40a6f55 ministry-driven decision refactor
AR-05 | P3 | Assoc Review — Triage | Non-school ministry → auto-forward chain (feeds TK-06) | 1. Approve an association with ministry=health_medical_education 2. Open the resulting Ticket in /tickets | Ticket exists with status=FORWARDED_TO_DEPT (auto-forwarded via forward_if_non_school). Dept officer can accept from their workspace. SLA fields still editable (see TK-06). | PASS | Verified on Railway
AR-06 | P3 | Assoc Review — Triage | School ministry → stays OPEN for PA to assign | 1. Approve an association with ministry=school_education_tamil_dev_info_publicity 2. Open the resulting Ticket | Ticket exists with status=OPEN. Assign panel visible so PA can route to one of the 10 school departments. Contrast with AR-05. | PASS | Verified on Railway
AR-07 | P3 | Assoc Review — Dismiss | Reject with reason + restore | 1. Reject a submission with reason 'incomplete documentation' 2. Verify status=REJECTED 3. Restore back to AWAITING_REVIEW | Reason preserved on the row. Restore reverses cleanly. Activity log records both actions. | PASS | Verified on Railway
T3-01 | P3 | UX | Polished error toasts across tickets + association review | 1. Trigger 4 failures: 5MB+ attachment, network offline mid-approve, backend 500, invalid edit 2. Screenshot each toast on both surfaces | Every message user-friendly. Zero tracebacks / raw HTTP codes / 'gemini-2.5-flash'. Routed through businessMessage() (errors.ts). | PASS | Verified on Railway
T3-02 | P3 | UX | Mobile viewport (375px) — both drawers usable | 1. Resize to 375x812 2. Open ticket drawer → try Assign / Comment / Add attachment 3. Open association drawer → try Approve / Ministry override | Both drawers scale / go full-screen. All actions reachable with thumbs. No horizontal body scroll. | PASS | Verified on Railway
EV-01 | P4 | Events — Access | Events login works with seeded events_reviewer credentials | 1. Log in to /dashboard/login as admin-office (seeds event_reviewer role) 2. Then log in to /events/login with the same credentials | Both logins succeed. events_session cookie set. No 401 / no 'unauthorized' with legitimate creds. | PASS | Verified on Railway | Verifies events_auth.py real-user path (env-credential path was removed — see prior incident)
EV-02 | P4 | Events — Access | Direct URL without events_session → clean redirect | 1. Wipe events_session cookie 2. Navigate to /events directly | Redirect to /events/login. No 500 / no blank page. | PASS | Verified on Railway
EV-03 | P4 | Events — Add | Manual event add (title / venue / date / note) → appears in list | 1. Open events UI, click Add Event 2. Fill title, venue, date, optional note 3. Save | New row in list. All fields populated. No AI extraction path fired for manual entry. | PASS | Verified on Railway
EV-04 | P4 | Events — Voice | Tamil voice add → 200 OK, extraction runs (SDK ASCII fix regression) | 1. Record a 20s Tamil voice describing an event 2. Upload via voice add flow | 200 OK. Extraction populates title_en / title_ta / venue / date. NO UnicodeEncodeError. NO 500 from the google-genai httpx header path. | PASS | Verified on Railway | Regression for event_service.py _ascii_safe fix (voice-note ASCII scrub before Gemini call)
EV-05 | P4 | Events — Voice | Tamil voice + Tamil note field → 200 OK | 1. Same as EV-04 2. Type Tamil text into the note field before upload | 200 OK. Note preserved on the event row. No header-encoding crash. | PASS | Verified on Railway
EV-06 | P4 | Events — Voice | English voice add → extraction runs | 1. Record 20s English voice describing an event 2. Upload | Extraction returns English title / venue. Row created. | PASS | Verified on Railway
EV-07 | P4 | Events — Photo | Photo add — invitation card image → OCR extraction | 1. Upload a photo of an invitation card 2. Wait for extraction | title / venue / date extracted; row appears in list with source doc viewable inline. | PASS | Verified on Railway
EV-08 | P4 | Events — Photo | Blurry / non-invitation image → polished error (businessMessage) | 1. Upload a random selfie / blurry image 2. Watch EventPopup / error toast | User-friendly message ('could not read'). NO Python traceback. NO 'gemini-2.5-flash' / 'codec' strings. | PASS | Verified on Railway | Regression for TECHNICAL regex + businessMessage() in EventPopup
EV-09 | P4 | Events — List | Default list shows upcoming events | 1. Load /events 2. Verify default view | Upcoming events (date >= today) sorted by date ascending. Past events hidden or in a separate section. | PASS | Verified on Railway
EV-10 | P4 | Events — List | Date range filter + search by title/venue | 1. Apply a date range → verify rows narrow 2. Search by partial title / venue name | Both narrow the visible set correctly. Clear-all restores. | PASS | Verified on Railway
EV-11 | P4 | Events — Detail | EventPopup opens on row click with bilingual content | 1. Click a Tamil-added event (has title_ta populated) 2. Toggle language | Popup shows title / venue / note in the selected language via title_ta / venue_ta fields. No mojibake. | PASS | Verified on Railway
EV-12 | P4 | Events — Detail | Error field renders polished text (businessMessage regression) | 1. Force an event to be in the error_message state (upload a bad file OR find a historically-failed event) 2. Open EventPopup | error_message rendered via businessMessage() — user-friendly text, not raw 'UnicodeEncodeError: ascii codec can't encode...' or 'gemini-2.5-flash failed on all models'. | PASS | Verified on Railway | Regression for 5bbbc1c EventPopup businessMessage() wiring + TECHNICAL regex
EV-13 | P4 | Events — Edit | Edit event fields → persists | 1. Open an existing event 2. Edit title / venue / date 3. Save; reload | Changes persist across reload. Activity log or last-updated stamp reflects the edit. | PASS | Verified on Railway
EV-14 | P4 | Events — Edit | Delete event → gone from list | 1. Delete an event (with confirmation) 2. Verify list | Row removed. No orphan attachments left in storage (soft delete OK if that's the design). | PASS | Verified on Railway
EV-15 | P4 | Events — Edit | Concurrent edit (two tabs) — clean last-write-wins | 1. Open same event in two tabs 2. Edit + save in tab A 3. Edit + save in tab B without refresh | Second save overwrites cleanly OR clean 'this event was updated elsewhere' message. No silent 500 / no lost data. | PASS | Verified on Railway
T4-01 | P4 | UX | All error toasts polished across the events surface | 1. Trigger failures: 5MB+ audio, 5MB+ image, network offline mid-upload, backend 500, invalid extract 2. Screenshot each toast | Every message user-friendly. Zero tracebacks / raw HTTP codes / 'gemini-*' / 'codec'. Routed through the businessMessage() polish path. | PASS | Verified on Railway
T4-02 | P4 | UX | Mobile viewport (375px) — record voice + view event usable | 1. Resize to 375x812 2. Try the voice-add recorder 3. Open EventPopup | Recorder buttons reachable. Popup scales / goes full-screen. No horizontal body scroll. | PASS | Verified on Railway
EX-01 | P5 | Exec Queue — Access | RBAC — office admin sees the queue, dept_officer redirected | 1. Log in as pa_admin → navigate to Executive Queue 2. Log in as dept_officer → try Executive Queue directly | pa_admin loads. dept_officer redirected to /tickets. No cross-role leak. | PASS | Verified on Railway
EX-02 | P5 | Exec Queue — List | List + filters + pill counts match current view | 1. Load queue → verify aggregated tickets across depts 2. Apply priority / dept / status filters 3. Check pill counts follow current filter (WYSIWYG) | Every filter narrows the visible set. Pill counts = list count for the same tab. SLA-breached chip also narrows. | PASS | Verified on Railway | Regression for 3f0df68 pill-count parity (was fixed on tickets, exec queue may share the pattern)
EX-03 | P5 | Exec Queue — Actions | Escalate action creates activity + notifies stakeholders | 1. Open an SLA-breached ticket 2. Click Escalate; add reason 3. Check activity log + notification dispatch | Activity row: action_type='escalated', actor=admin, reason preserved. Notification fires (log line visible). | PASS | Verified on Railway
EX-04 | P5 | Exec Queue — Actions | SLA-breached chip filter — WYSIWYG count | 1. Note the breached chip count 2. Apply a filter that narrows the queue 3. Verify chip count updates to match the filtered view | Breached chip counts current filter set (0cde4ed reversal — chip is filter-aware, not office-wide). | PASS | Verified on Railway | Regression for 0cde4ed
DP-01 | P5 | Dept — Access | dept_officer login → sees only own dept's tickets | 1. Log in as a dept_officer (dept_a) 2. Try to open a ticket from dept_b directly via URL | dept_a's tickets visible. dept_b's ticket → 403 with clean 'not authorized' message (not 500). | PASS | Verified on Railway | Regression for f40c2f6 HTTPException import fix (clean 403 not 500)
DP-02 | P5 | Dept — Lifecycle | Accept flow — status → IN_PROGRESS, accepted_at + accepted_by set | 1. Open a ticket routed to caller's dept in ASSIGNED state 2. Click Accept 3. Verify state + activity log | Ticket.status = IN_PROGRESS. accepted_at / accepted_by populated. Activity row action_type='department_accepted'. | PASS | Verified on Railway
DP-03 | P5 | Dept — Lifecycle | Progress update — note + optional pct | 1. On an IN_PROGRESS ticket, post a progress update with a note + 40% pct 2. Verify activity log + ticket state | Activity row: action_type='progress_update', note preserved, payload.progress_pct=40. Ticket.progress_pct=40. | PASS | Verified on Railway
DP-04 | P5 | Dept — Lifecycle | Forward to another dept — reason required, cannot self-forward | 1. On an owned ticket, click Forward → target = own dept → expect reject 2. Forward without reason → expect reject 3. Forward to dept_b with reason 'requires their expertise' | Self-forward returns 400 'Cannot forward to the same department'. No reason returns 400 'A reason is required'. Valid forward: status=ASSIGNED, department=dept_b, accepted_at cleared, activity 'department_forwarded' with reason in payload. | PASS | Verified on Railway
DP-05 | P5 | Dept — Lifecycle | Resolve — mandatory remarks + at least one proof attachment | 1. On IN_PROGRESS, click Resolve without remarks → reject 2. Add remarks, no attachment → reject 3. Add remarks + one proof file → succeed | Both empty cases return 400 with clean message. Valid resolve: status=RESOLVED, remarks stored, attachment linked, activity 'resolved'. | PASS | Verified on Railway
DP-06 | P5 | Dept — Attachments | All three attachment namespaces resolve correctly for dept | 1. Open a ticket derived from an AI upload → click the citizen's original PDF (ai_uploads/…) 2. Open an appointment attachment (attachments/…) 3. Open a ticket attachment uploaded by PA (ticket_attachments/…) 4. Try a proposals/ URL — expect 403 | First three render inline (200). proposals/ → 403 (no UI for it). Dept activity trail includes upload if they added one — regression for 7fd0118. | PASS | Verified on Railway | Combines cbc9c8c (ai_uploads/ branch) + 7fd0118 (dept-add-attachment threads ticket_id + actor) + fail-closed defaults
DP-07 | P5 | Dept — Lifecycle | Reopen from PA side → ticket comes back to dept | 1. Dept resolves a ticket 2. PA reopens it via ticket drawer 3. Verify state on dept portal | Ticket.status=REOPENED, visible again in dept's active list. Activity log has both 'resolved' and 'reopened' rows. | PASS | Verified on Railway
MN-01 | P5 | Minister — Access | Minister login → PWA loads with service worker | 1. Log in via /minister/login 2. Verify /minister/sw.js registers cleanly 3. Check service worker scope | Login sets minister_session. /minister/sw.js served with Content-Type application/javascript + Service-Worker-Allowed: /minister/ (next.config.mjs headers). PWA installable. | PASS | Verified on Railway
MN-02 | P5 | Minister — Read-only | No mutation controls visible — read-only surface | 1. Open a ticket / association / proposal on the minister PWA 2. Scan for edit / assign / approve / reject buttons | Zero mutation controls. Only view + navigation. Attempting a mutation API call via devtools → 403. | PASS | Verified on Railway
MN-03 | P5 | Minister — File access | /api/files → /minister/api/files URL rewrite works | 1. Open a ticket with an attachment 2. Inspect the attachment URL in devtools | URLs in the payload rewritten from /api/files/… to /minister/api/files/… (minister.py:208). Fetch succeeds via minister_session cookie. | PASS | Verified on Railway | Regression for the deep-rewrite pattern in minister.py
MN-04 | P5 | Minister — File access | Attachment preview iframe renders (CI-89 regression from minister surface) | 1. Open a ticket / association with a PDF attachment on the minister PWA 2. Verify the iframe renders | PDF renders inline (not 'blocked:other'). /minister/api/files/… is in the middleware's embeddable-prefix list (see main.py _EMBEDDABLE_PREFIXES). | PASS | Verified on Railway
MN-04b | P5 | Minister — File access | Event photos + audio render on minister PWA (events/ namespace) | 1. Open /minister/events 2. Click an event with a photo → verify image renders 3. Play an event's voice audio → verify it streams | Both render (200). Prior bug: 403 because minister._authorize had no `events/` branch and fell through to fail-closed deny. Sentinel keys like `events/manual` still 403 (no actual bytes). | PASS | Verified on Railway | USER-REPORTED. Fixed by adding events/ branch to minister._authorize gated on InvitationEvent.image_path OR audio_path == key.
MN-05 | P5 | Minister — Scoping | Ministry-scoped view — sees only assigned-ministry rows | 1. Log in as a minister assigned to ministry X 2. Load list — verify all rows are ministry-X 3. Try to open a ticket from ministry Y directly | List filtered to ministry X only. Direct-URL to another ministry's ticket → 403 / redirect, not silent view. | PASS | Verified on Railway
T5-01 | P5 | Cross-cutting | RBAC gates on all escalation endpoints (Group 3 audit) | 1. For each of the 6 escalation endpoints (accept / forward / progress / resolve / reopen / escalate), try calling as an unauthorized role 2. Expect 403 on every one | Every endpoint gates by role. dept_officer can't hit exec-only routes. minister can't mutate. Cross-dept dept_officer gets 403 on other-dept tickets. | PASS | Verified on Railway | Regression for Group 3 RBAC hardening (audit fix batch)
T5-02 | P5 | Cross-cutting | i18n copy — no 'referral' vocabulary drift in exec/dept surfaces | 1. Scan the Executive Queue + Dept portal UI 2. Look for stray 'referral' / 'refer' terms | Zero 'referral' vocabulary — replaced with 'petition' / 'case' / 'ticket' terminology per 2599564. Consistent with citizen-facing form. | PASS | Verified on Railway | Regression for 2599564 i18n(exec-queue) cleanup
T5-03 | P5 | Cross-cutting | Polished error toasts across all three surfaces | 1. Trigger failures on Exec Queue, Dept portal, Minister PWA 2. Screenshot each toast | Every message user-friendly. Zero tracebacks / raw HTTP codes / 'gemini-*'. Routed through businessMessage() (errors.ts). | PASS | Verified on Railway
T5-04 | P5 | Cross-cutting | Mobile viewport (375px) — Minister PWA usable | 1. Resize to 375x812 2. Log in as minister → open a ticket 3. Verify layout + interaction | PWA scales to mobile. Nav + drawers usable with thumbs. No horizontal body scroll. Service worker still registered. | PASS | Verified on Railway
P6-01 | P6 | Auth boundaries | Cross-role RBAC sweep on the 6 escalation endpoints | 1. Enumerate: accept / forward / progress / resolve / reopen / escalate 2. For each, call as pa_admin, dept_officer (own dept), dept_officer (other dept), minister, unauth 3. Verify allow/deny matrix | pa_admin: accept ❌ (dept only) / forward ❌ / progress ❌ / resolve ❌ / reopen ✅ / escalate ✅. dept_officer own: all ✅. dept_officer other: all 403. minister: all 403. unauth: 401 / login redirect. | PENDING |  | Regression for Group 3 RBAC hardening + f40c2f6 clean 403
P6-02 | P6 | Auth boundaries | Session cookies — HttpOnly + Secure + SameSite | 1. Log in on each surface (PA / dept / minister / events / crowd) 2. Inspect Set-Cookie headers in devtools | Every session cookie has HttpOnly, Secure (in prod), and SameSite=Lax or Strict. No cookie readable from JS. | PENDING
P6-03 | P6 | Rate limit | RATE_LIMIT_ENABLED master switch respected | 1. Confirm current env has RATE_LIMIT_ENABLED=false — burst 20 requests, verify no 429 2. If desired, flip to true in a separate env — verify @limiter.limit endpoints return 429 on burst | OFF: no rate limiter fires anywhere. ON: individual @limiter.limit endpoints return 429 at their configured rates (3-5/min per IP). | PENDING |  | Skipped-in-P1 CI-23 setup validated at the system level
P6-04 | P6 | Perf | GZip compression on JSON responses (>1KB) | 1. curl -H 'Accept-Encoding: gzip' <api endpoint returning >1KB JSON> 2. Verify Content-Encoding: gzip in response headers | Responses >1KB are gzipped. Small (<1KB) responses not gzipped. GZipMiddleware minimum_size=1024 respected. | PENDING |  | Regression for PERF-17 GZipMiddleware
P6-05 | P6 | Perf | /api/venues cache — short public + revalidate | 1. curl /dashboard/api/venues → inspect Cache-Control header 2. Repeat within cache window → verify 304 or served from cache | Cache-Control: public, max-age=<short>, must-revalidate (or similar). Not immutable, not no-store. Frontend fetch config no longer sends no-cache. | PENDING |  | Regression for PERF-18
P6-06 | P6 | Perf | Immutable file cache invalidates on same-key overwrite | 1. Upload a PDF, note ETag on GET /dashboard/api/files/<key> 2. Overwrite the same key with different bytes (via internal MinIO or admin flow) 3. GET again — verify ETag changed → browser refetches | ETag = md5(file_path + size + last_modified + media_type). A same-size overwrite still invalidates because last_modified changed. Cached copies never serve stale bytes. | PENDING |  | Regression for the ETag rebuild fix
P6-07 | P6 | Time | IST/UTC drift-free — daily loops + counts + tokens agree on 'today' | 1. At 23:55 IST (18:25 UTC), submit a petition 2. Check /counts today bucket + referral daily token + convert-to-petition daily guard 3. Wait until 00:05 IST next day, repeat | All three surfaces treat 'today' as the IST calendar day, not UTC. No off-by-one at day boundaries. | PENDING |  | Regression for CORR-07/08/09 IST/UTC drift
P6-08 | P6 | Time | Background task survival — spawn_bg tasks complete | 1. Trigger a summarisation via appointment submit 2. Immediately check _BG_TASKS module-level set is retained until task completes 3. Verify GrievanceSummaryRecord row lands even under concurrent load | spawn_bg tasks aren't GC'd mid-flight. Every submitted appointment eventually has a GSR row (unless SDK error). | PENDING |  | Regression for CORR-01/02 spawn_bg GC hardening
P6-09 | P6 | Security headers | Non-file responses stay strict: DENY + frame-ancestors 'none' | 1. curl /dashboard/api/tickets → inspect headers 2. Repeat for /api/v1/appointments, /minister/api/tickets, jinja pages | Every non-file response has X-Frame-Options: DENY, CSP frame-ancestors 'none', X-Content-Type-Options: nosniff, Referrer-Policy: strict-origin-when-cross-origin, Permissions-Policy present. | PENDING |  | Regression for _SecurityHeadersMiddleware baseline
P6-10 | P6 | Security headers | File-serve responses: SAMEORIGIN + frame-ancestors 'self' <CORS> | 1. curl /dashboard/api/files/<key> → inspect headers 2. Same for /events/api/files, /minister/api/files, /department/api/files | All four prefixes return X-Frame-Options: SAMEORIGIN and CSP frame-ancestors containing 'self' + CORS_ORIGINS entries. Cross-checks the CI-89 iframe fix from every embeddable-asset entry point. | PENDING |  | Regression for 38a64bc scoped iframe relaxation
P6-11 | P6 | AI reliability | Vertex → direct-API fallback + polished error on both-fail | 1. Confirm boot log shows 'Vertex AI backend ready (creds=env-content)' — Vertex is primary 2. Force-fail Vertex temporarily → verify direct-API takes over 3. Force both to fail → verify polished user-facing error (no traceback) | Log line at boot confirms creds source. Vertex outage triggers direct-API fallback silently. Both-fail returns 502 with human message; no raw 'gemini-*' or SDK exception in UI. | PENDING |  | System-wide re-verify of the Vertex overload (commit 6fda89b) + fail-through path
P6-12 | P6 | File caps | MAX_FILE_SIZE_MB + MAX_ATTACHMENTS enforced at every upload path | 1. Try uploading a 6MB file via: citizen QR upload, PA drawer, dept drawer, event photo 2. Try uploading an 11th file on an appointment with 10 existing attachments | Every path returns clean 4xx with human message. 5MB cap + 10-file per submission cap honoured across surfaces. | PENDING
P6-13 | P6 | Filename hygiene | Filename sanitization consistent across upload paths | 1. Try uploading '<script>alert(1)</script>.pdf', '../../etc/passwd.pdf', a 500-char name via each entry point 2. Verify storage key + display + PDF preview title all safe | All entry points route through _sanitize_filename. Path traversal never escapes uploads/. XSS in filename escaped everywhere it's rendered. No 500 on very long names. | PENDING |  | CITZ-02 regression, cross-surface
P6-14 | P6 | PII at rest | Citizen mobile encrypted + blind-indexed + masked on read | 1. Submit an appointment with a specific mobile (e.g. 9876543210) 2. Query the DB — verify encrypted_mobile is Fernet-encrypted (not plaintext), mobile_blind_index is a hex hash 3. Open the appointment in every UI surface — verify mobile shown as ******3210 | Plaintext mobile never in DB. Blind index enables dedup lookups. Every read surface masks the mobile — PA drawer, dept drawer, minister PWA, activity log, list rows. | PENDING
P6-15 | P6 | Prod safety | assert_production_ready refuses on unsafe defaults | 1. Simulate each unsafe config in isolation: placeholder SECRET_KEY, default staff creds, localhost in CORS_ORIGINS, short SECRET_KEY, COOKIE_SECURE=false in prod 2. Verify startup refuses with clear message | Each unsafe default triggers a startup abort with a message pointing at the exact config. TestProdReadyGates in tests/test_pre_prod_fixes.py covers this at unit level; verify runtime behaviour matches. | PENDING |  | Regression for Group 2 prod-safety hardening + the config.py DEBUG-remote-DB guard (currently disabled per user's intentional edit at config.py:293)